Project Plan: TrackBudget

Project Manager: Mohamed Elgasim Project Sponsor: Commerce Bank

Development Team: Miguel Flores (Backend), Hashim Abdulla (Frontend), Pavan Krishna (Database)

Project Timeline: February 9, 2026 – May 8, 2026

Repository: GitHub - TrackBudget (https://github.com/mohamede2022/TrackBudget/tree/main)

1. Project Overview

TrackBudget is a full-stack web application designed to help users effectively track and manage their finances. Our goal is to provide a dedicated financial component with high usability for diverse groups, including students and businesses. We are building this without reliance on Content Management Systems (CMS), prioritizing a custom, secure experience.

2. Resources Needed

To successfully execute this project, we rely on the following resources:

- Human Resources: A four person development team structured into specific roles (Project Manager, Backend Programmer, Frontend Programmer, and Database Manager). We are assuming all team members have sufficient proficiency in Python and Flask to execute their tasks.

- Technology Stack (Backend): Python and Flask.

- Technology Stack (Database): MySQL is strictly required for database management, utilizing drivers like pymysql or mysqlclient.

- Technology Stack (Frontend): At least one CSS framework and one JavaScript framework/library.

- Third Party Integrations: An API key or open source model is required to power the LLM AI Assistant feature. Mock banking data will be used for the financial demonstrations.

- Version Control: GitHub for repository management and code integration.

3. Timeline & Major Milestones

The project extends roughly three months, broken down into two-week sprint cycles to ensure steady progress and allow for necessary testing.

- Milestone 1 (Feb 23, 2026): Infrastructure and secure authentication deployed.

- Milestone 2 (Mar 10, 2026): Core financial component and user dashboard active.

- Milestone 3 (Mar 24, 2026): Database expanded for user types and initial visual identity applied.

- Milestone 4 (Apr 07, 2026): Advanced security validation and error handling finalized.

- Milestone 5 (Apr 21, 2026): AI backend infrastructure connected and frontend UI polished.

- Milestone 6 (May 05, 2026): Functional AI chat interface complete.

- Final Delivery (May 08, 2026): Project handover/presentation to Commerce Bank.

4. Detailed Tasks & Dependencies (Sprint Breakdown)

Sprint 1: System Architecture & Secure Authentication (Feb 19 - Feb 29)

- Tasks: * Deploy the MySQL database for user profiles.

- Set up the Python/Flask environment.

- Implement user registration and login endpoints.

- Apply password hashing (e.g., Flask-Bcrypt) to ensure credentials are never stored in plain text.

- Build responsive base frontend pages using the chosen CSS framework.

- Dependencies: None. This is the foundational sprint.

Sprint 2: Core Financial Component & Dashboard (Mar 1 - Mar 13)

- Tasks: * Develop the Central Dashboard to display an overview of financial health.

- Create the User Management page for profile settings.

- Expand MySQL to hold financial data and transaction history.

- Implement logic for budget tracking and payment monitoring.

- Dependencies: Requires Sprint 1 database schema and secure login system to be fully functional.

Sprint 3: User Identity & Type Definition (Mar 14 - Mar 24)

-Tasks: * Add a new database table for specific user types (Student, Default, Business).

- Integrate the official website logo into the UI.

- Update backend logic to assign user types upon registration.

- Dependencies: Relies on the Sprint 1 user table to establish foreign key relationships.

Sprint 4: Validation & Security Requirements (Mar 25 - Apr 07)

-Tasks: * Implement strict password requirement parameters on the frontend.

- Develop backend checks to prevent duplicate emails and usernames in the system.

- Fix account creation messaging so logic perfectly matches between the frontend and database.

- Dependencies: Requires the completed registration flow from Sprints 1 and 3.

Sprint 5: AI Infrastructure & UX Polish (Apr 08 - Apr 21)

- Tasks: * Initialize the connection to the LLM via API for the AI Financial Assistant.

- Establish a read-only database view so the AI can safely parse transaction data.

- Implement animations for the password requirements on the frontend.

- Draft system instructions (Prompt Engineering) to keep the AI focused on financial assistance.

- Dependencies: Needs the mock data generated in Sprint 2  and the polished UI/error handling from Sprint 4.

Sprint 6: Integrated AI Assistant (Apr 22 - May 05)

- Tasks: * Build out a responsive chat interface on the frontend.

- Finalize AI logic to answer specific user questions about their financial data.

- Create a database table to store user-AI chat logs for context retention.

- Dependencies: Completely dependent on the successful LLM API integration established in Sprint 5.

5. Key Deliverables

By the end date of May 8, 2026, our team will deliver the following to Commerce Bank:

- Fully Functional Web Application: Accessible via browser, featuring secure user registration, login, and profile editing capabilities.

- Core Financial Tools: Working components for budgeting and monitoring payments.

- Adaptive Dashboard: An aligned, readable UI that adjusts based on whether the user is a student or business.

- AI Financial Assistant: An integrated chat interface allowing users to ask questions regarding their mock financial data.

- Source Code & Documentation: All code pushed to our central GitHub repository, alongside requirements, design diagrams, and this project plan.